## ReadMe & Instructions
TheConsultAI - Enterprise AI Roadmap Template
A 12-month production-focused framework for scaling cognitive architectures.
INSTRUCTIONS FOR USE:
1. This roadmap outlines a standard 12-month enterprise AI rollout.
2. Review the four core phases: Alignment, Validation, Integration, and Production MLOps.
3. Adjust the Start and End Dates on the 'Roadmap' sheet to match your organizational timelines.
4. Assign single-owner accountability for each key milestone to avoid delivery friction.
5. Update 'Status' periodically to track implementation progress.
PHASE OVERVIEWS:
• Phase 1: Strategy & Alignment (Months 1-2) — Define KPIs, compute initial ROI, build board approval deck.
• Phase 2: PoC & Validation (Months 3-4) — Clean core data pipelines, test RAG vs fine-tuning assumptions.
• Phase 3: Scaling & Integration (Months 5-8) — Connect models to enterprise CRM/ERP systems, design UI/UX.
• Phase 4: Production & MLOps (Months 9-12) — Secure deployments, set drift monitoring, launch hypercare.

## Roadmap
ID | Phase | Task / Milestone Name | Owner | Start Month | End Month | Status | Dependencies | Outcome Benchmark
1.1 | Phase 1: Alignment | Define executive KPIs and measurable outcomes | CIO/Sponsor | 1 | 1 | Completed | None | Board alignment on 12-month goals
1.2 | Phase 1: Alignment | Select first 3 high-impact use cases | AI Architect | 1 | 2 | Completed | 1.1 | Scoping documents signed off
1.3 | Phase 1: Alignment | Form governance, risk & security committee | CISO | 2 | 2 | In Progress | 1.1 | Compliance checklist approved
2.1 | Phase 2: Validation | Ingest and structure core unstructured data | Data Lead | 3 | 4 | Not Started | 1.2 | Data lake pipelines active
2.2 | Phase 2: Validation | Build RAG prompt engineering sandbox | Engineer Lead | 3 | 4 | Not Started | 2.1 | Working prototype in sandbox
2.3 | Phase 2: Validation | Run model latency and cost analysis | AI Architect | 4 | 4 | Not Started | 2.2 | Optimal model selection report
3.1 | Phase 3: Integration | Connect model APIs to internal CRM/ERP | Integration Eng | 5 | 7 | Not Started | 2.2 | Connected test environment active
3.2 | Phase 3: Integration | Build conversational enterprise UI | UX Lead | 6 | 7 | Not Started | 3.1 | High-fidelity user interface built
3.3 | Phase 3: Integration | Conduct user acceptance testing (UAT) | QA Lead | 8 | 8 | Not Started | 3.2 | UAT sign-off from business units
4.1 | Phase 4: Production | Deploy production infrastructure (Docker/Kubernetes) | DevOps Lead | 9 | 10 | Not Started | 3.3 | Containerized deployment running
4.2 | Phase 4: Production | Establish MLOps drift and alert dashboards | MLOps Lead | 10 | 11 | Not Started | 4.1 | Real-time accuracy alerts configured
4.3 | Phase 4: Production | Trigger user training and 90-day hypercare | Change Manager | 11 | 12 | Not Started | 4.2 | 100% team onboarding completed